## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
S1 | S1 | 1 | Fundamentals and Prequsites to work with Project | MUST HAVE | No Dependency | Bella Gnana Charmika | 3- Completed
S2 | S2 | 2 | Understanding the Project, Project environment setup and Database integration | MUST HAVE | MySQL / initial DB schema | Bella Gnana Charmika | 3- Completed
S3 | S3 | 3 | Parallel Text Handling | SHOULD HAVE | Depends on DB integration (US ID 3) | Bella Gnana Charmika | 3- Completed
S4 | S5 | 4 | Paralelle text Loading, Breaking, Grouping, Searching & Integration | SHOULD HAVE | Depends on US ID 4 | Bella Gnana Charmika | 3- Completed
Note on F1: ====== ID#AAABs5CmnRc Sumeet Kumar Barua08 (2025-01-27 09:44:41) Mention the US ID(s) on which the user story depends.

## Sprint Backlog
w
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | 1 | Fundamentals and Prequsites to work work with Project | Sep 18th | 2nd Oct | Bella Gnana Charmika | Learning and Practicing Fundamentals | Done |  | Introduction |  |  | Python and Jupyter Installation | keywords and naming conventions | Naming convention | Flow Control | Went through running notes | python string | Functions | Functions Part 1 | Functions Part 2 | Python Modules | OOPS
2 | 2 | Understanding the Project, Project environment setup and Database integration | 3rd Oct | 17th Oct | Bella Gnana Charmika | Leaning Multi-Processing and Project Understanding | Done |  | OOPS | went through notes | recap through materials | Packages | Multi Processing concept with Examples | Continued Multi Processing and Pipe | Practiced MultiProcessing and Pipe | Introduction and understanding the project | Interative Session on Project | environment and SQLite setup | completed SQLite setup | Interactive Session on uderstanding project | Multitasking in Python | Practiced previous sessions
3 | 3 | Parellel Text Handling | 18th Oct | 1st Nov | Bella Gnana Charmika | practicing workflows and establishing the core project setup | Done |  | practied | practiced | went through running notes | Introduced to python Multitasking | Thread Pool Executer | went through materials | Regex overview | practiced multi tasking | Practiced Thread pool executor | Text Handling(Regex) | Practiced on Regex | Execution flow of Regex with practical output | Rule Based Tagging | Hands on code walkthrough(project)
4 | 4 | Paralelle text Loading, Breaking, Grouping, Searching & Integration | 2nd Nov | 16th Nov | Bella Gnana Charmika | Practicing Text Breaking ang grouping and project setup | Done |  | Reacap hands on code | Completed Hands on code | Text Breaking and Grouping | Practiced hand on code | Continued Text Breaking and Grouping | Milestone2 code Walkthrough | went through materials | Text breaking & grouping | Text with big texts & performance optimization | Milestone2 cod walkthorough | session onProgress, Upcoming plans and github | Milestone3 : SMTP Library | implemwnting the sample programs | revised the previous concepts
Note on D2: ====== ID#AAABs5CmnRY Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on E2: ====== ID#AAABs5CmnQ4 Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on I3: ====== ID#AAABs5CmnRA Sumeet Kumar Barua08 (2025-01-27 09:44:41) This is the total task estimated in hours for all the user stories
Note on J3: ====== ID#AAABs5CmnQ0 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 1 work
Note on K3: ====== ID#AAABs5CmnQg Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 2 work
Note on L3: ====== ID#AAABs5CmnQk Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 3 work
Note on M3: ====== ID#AAABs5CmnRE Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 4 work
Note on N3: ====== ID#AAABs5CmnRU Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 5 work
Note on O3: ====== ID#AAABs5CmnRI Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 6 work
Note on P3: ====== ID#AAABs5CmnQs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 7 work
Note on Q3: ====== ID#AAABs5CmnQ8 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 8 work
Note on R3: ====== ID#AAABs5CmnQw Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 9 work
Note on S3: ====== ID#AAABs5CmnRg Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 10 work
Note on T3: ====== ID#AAABs5CmnRM Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 11 work
Note on U3: ====== ID#AAABs5CmnQo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 12 work
Note on V3: ====== ID#AAABs5CmnRQ Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 13 work
Note on W3: ====== ID#AAABs5CmnRk Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 3 | Day 9 | Unclear specification for “parallel text handling” — i.e. what constitutes a “parallel text pair”, how to mark language pairs | Held a quick alignment meeting with team/mentor; documented clear definition and acceptance criteria for “parallel text pair” (source–target), included in user story description
Sprint 3 | Day 10 | Parser failing on some text files due to unexpected formats (e.g. extra whitespace, inconsistent separators) | Updated parser to include robust pre-sanitization (trim whitespace, normalize separators), added validation checks before processing
Sprint 4 | Day 13 | Some parallel text files too large — causing memory overflow / slow processing when grouping/searching | Refactored processor to handle streaming/chunk-based reading instead of loading whole file; added chunk-by-chunk processing to reduce memory usage
Sprint 4 | Day 14 | Edge-cases: pairs where target text missing or misaligned — causing incorrect grouping or null entries in output | Added fallback logic: if a parallel segment missing or empty, skip that entry and log a warning; updated user-story acceptance criteria to include “skip incomplete pairs” behavior
Sprint 4 | Day 15 | Integration issue: Output format (grouped pairs) did not match expected schema for downstream workflow & search module | Collaborated with integration lead to define exact output schema (field names, encoding, delimiters), revised output formatting accordingly; added unit tests for format compliance
Sprint 4 | Day 16 | Search functionality ambiguous: should search across all languages? case-insensitive? phrase vs word match? — causing confusion for testers | Conducted team discussion to finalize search requirements: default to case-insensitive word match, with optional exact or regex search; updated documentation and user-story acceptance criteria
Sprint 4 | Day 17 | Lack of documentation / module description — other team members unable to reuse or extend the parallel-text processor code | Created README and module-level doc (input format, output format, assumptions, limitations), added code comments and sample usage examples

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint 1 | 2025-09-18 | 2025-10-02 | Bella Gnana Charmika | Learning and practicing fundamentals | Spending too much time on unstructured setup / procrastinating setup steps | Maintain consistent focus on fundamentals & environment setup | Fundamentals and prerequisites learned and setup done (environment, project setup)
2 | Sprint 2 | 2025-10-03 | 2025-10-17 | Bella Gnana Charmika | Learning multi-processing & project understanding / DB integration | Working piecemeal without clear plan → Stop jumping between tasks | Continue building strong project foundation through proper environment & database integration | Fundamentals and prerequisites learned and setup done (environment, project setup)
3 | Sprint 3 | 2025-10-18 | 2025-11-01 | Bella Gnana Charmika | Practicing workflows — parallel text handling | Stop delaying integration of parallel text handling (or stop last-minute rushing) | Continue exploring and refining parallel text handling workflows | Parallel text handling module setup done
4 | Sprint 4 | 2025-11-02 | 2025-11-16 | Bella Gnana Charmika | Practicing text loading, breaking, grouping & integration | Stop doing manual grouping/searching without automation/standardization (if that was attempted manually first) | Continue building on integration efforts, modularizing text processing & preparing for next modules | Text loading, breaking, grouping and integration prototype done